## Agile Template
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Requirement gathering and problem statement definition for Clario (AI-powered real-time customer support coaching assistant) | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S1 | S1 | US-002 | Workflow creation, system architecture design and project goal document | MUST HAVE | Lucid Chart | Jasir Ahamed | 3- Completed
S1 | S1 | US-003 | Document discussion (Agile Template, Defect Tracker, Unit Test Plan) | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S2 | S2 | US-004 | Tech stack finalization: FastAPI, React/TypeScript/Vite/Tailwind, MongoDB, ChromaDB | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S2 | S2 | US-005 | Setup FastAPI backend project structure and MongoDB connection | MUST HAVE | MongoDB Atlas | Jasir Ahamed | 3- Completed
S2 | S2 | US-006 | Setup React/TypeScript/Vite/Tailwind frontend project structure | MUST HAVE | Node.js, Vite | Jasir Ahamed | 3- Completed
S3 | S3 | US-007 | Integrate Groq API (Llama 3.3 70B) for Simulator Agent (customer conversation simulation) | MUST HAVE | Groq API | Jasir Ahamed | 3- Completed
S3 | S3 | US-008 | Integrate Groq API for Intent/Sentiment Analysis Agent | MUST HAVE | Groq API | Jasir Ahamed | 3- Completed
S3 | S3 | US-009 | Integrate Google Gemini API for Knowledge Agent (RAG-based knowledge retrieval) | MUST HAVE | Gemini API, ChromaDB | Jasir Ahamed | 3- Completed
S4 | S4 | US-010 | Integrate Google Gemini API for Coaching Agent (real-time coaching suggestions) | MUST HAVE | Gemini API | Jasir Ahamed | 3- Completed
S4 | S4 | US-011 | Integrate Google Gemini API for Escalation Agent and Summary Agent | MUST HAVE | Gemini API | Jasir Ahamed | 3- Completed
S4 | S4 | US-012 | Setup ChromaDB vector store for RAG pipeline and knowledge base embeddings | MUST HAVE | ChromaDB | Jasir Ahamed | 3- Completed
S5 | S5 | US-013 | Build multi-agent orchestration pipeline connecting Simulator, Intent/Sentiment, Knowledge, Coaching, Escalation and Summary agents | MUST HAVE | US-007 to US-012 | Jasir Ahamed | 3- Completed
S5 | S5 | US-014 | Implement session persistence using global SessionContext with useReducer | MUST HAVE | React Context API | Jasir Ahamed | 3- Completed
S5 | S5 | US-015 | Design and build real-time chat/coaching UI with live agent feedback panel | MUST HAVE | Tailwind CSS | Jasir Ahamed | 3- Completed
S6 | S6 | US-016 | Implement Manual Mode (agent-guided manual conversation handling) | SHOULD HAVE | US-013 | Jasir Ahamed | 3- Completed
S6 | S6 | US-017 | Implement Replay Mode (review and replay past coaching sessions) | SHOULD HAVE | US-013, MongoDB | Jasir Ahamed | 3- Completed
S6 | S6 | US-018 | Workflow automation and optimization across agent pipeline | SHOULD HAVE | VS Code | Jasir Ahamed | 3- Completed
S7 | S7 | US-019 | Fix pipeline ordering bug - Intent/Sentiment analysis executing before Simulator message generation (one-turn lag) | MUST HAVE | US-013 | Jasir Ahamed | 3- Completed
S7 | S7 | US-020 | Fix turn index collision causing duplicate turn labels in generated reports | MUST HAVE | MongoDB schema | Jasir Ahamed | 3- Completed
S7 | S7 | US-021 | Fix markdown bleed-through in coaching agent output rendering | SHOULD HAVE | Frontend renderer | Jasir Ahamed | 3- Completed
S7 | S7 | US-022 | Fix report _id mismatch breaking UI report-selection state | MUST HAVE | MongoDB, React state | Jasir Ahamed | 3- Completed
S7 | S7 | US-023 | Resolve blocking synchronous calls on the async FastAPI event loop | MUST HAVE | FastAPI, asyncio | Jasir Ahamed | 3- Completed
S8 | S8 | US-024 | Full repository audit and end-to-end testing across all four milestones | MUST HAVE | US-001 to US-023 | Jasir Ahamed | 3- Completed
S8 | S8 | US-025 | Generate 17-page professional PDF project report with custom SVG architecture diagrams | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S8 | S8 | US-026 | Prepare 15-page Word technical report and one-page demonstration handout | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S8 | S8 | US-027 | Deployment and final submission to Infosys team via GitHub repository | MUST HAVE | Render/Hosting | Jasir Ahamed | 2- In Progress