## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Jasir Ahamed | 10-Jul-2026 | Pipeline ordering bug: Intent/Sentiment analysis agent ran before the Simulator agent generated its message, causing a perpetual one-turn lag in analysis results. | S7 | Jasir Ahamed | Logic Error | Reordered async pipeline execution so Simulator message generation completes before Intent/Sentiment analysis is triggered; added await sequencing. | 12-Jul-2026 | Closed | Verified across 10 test conversations, no lag observed.
2 | Jasir Ahamed | 11-Jul-2026 | Turn index collision producing duplicate turn labels in generated session reports. | S7 | Jasir Ahamed | Data/Logic Error | Introduced a unique monotonic turn-index generator tied to session ID instead of relying on array length; updated MongoDB schema. | 13-Jul-2026 | Closed | Regression tested with concurrent sessions.
3 | Jasir Ahamed | 13-Jul-2026 | Markdown bleed-through in Coaching Agent output - raw markdown symbols (*, #, -) visible instead of rendered formatting in the UI. | S7 | Jasir Ahamed | UI/Rendering | Added a markdown sanitizer/renderer (react-markdown) on the frontend to properly parse Gemini's markdown output before display. | 14-Jul-2026 | Closed | Verified on Chrome, Edge and Firefox.
4 | Jasir Ahamed | 15-Jul-2026 | Report _id mismatch between MongoDB document and frontend state causing UI report-selection to break after refresh. | S7 | Jasir Ahamed | Data Consistency | Standardized _id serialization (ObjectId to string) across API responses; updated SessionContext reducer to match on the corrected ID. | 16-Jul-2026 | Closed | Confirmed report selection persists after refresh.
5 | Jasir Ahamed | 17-Jul-2026 | Blocking synchronous calls (e.g. requests library, sync DB calls) on the FastAPI async event loop causing latency spikes during multi-agent orchestration. | S7 | Jasir Ahamed | Performance | Replaced blocking calls with async equivalents (httpx.AsyncClient, motor for MongoDB) and wrapped unavoidable sync calls in run_in_executor. | 18-Jul-2026 | Closed | Response latency reduced significantly under load test.
6 | Jasir Ahamed | 19-Jul-2026 | Session state lost on page refresh due to lack of centralized state management in early React implementation. | S5 | Jasir Ahamed | Functional | Implemented global SessionContext using useReducer to centralize and persist session state across components. | 20-Jul-2026 | Closed | Verified session persists across navigation and refresh.
7 | Jasir Ahamed | 21-Jul-2026 | Circular import error encountered when merging FastAPI route modules during a mid-project refactor. | S6 | Jasir Ahamed | Build/Import Error | Switched to full-file overwrites for affected modules instead of partial merges; restructured imports to remove circular dependency. | 21-Jul-2026 | Closed | Backend starts cleanly with no import errors.
8 | Jasir Ahamed | 22-Jul-2026 | Manual Mode occasionally skipped Escalation Agent trigger when sentiment score crossed the negative threshold. | S6 | Jasir Ahamed | Logic Error | Fixed conditional check on sentiment threshold comparison (was using strict inequality instead of inclusive) in Escalation Agent trigger logic. | 23-Jul-2026 | Closed | Verified escalation triggers correctly at threshold boundary.
9 | Jasir Ahamed | 24-Jul-2026 | Replay Mode failed to load older sessions stored before the _id serialization fix. | S8 | Jasir Ahamed | Data Consistency | Added a migration script to normalize legacy MongoDB document IDs to the corrected string format. | 25-Jul-2026 | Closed | All legacy sessions load correctly in Replay Mode.
10 | Jasir Ahamed | 26-Jul-2026 | ChromaDB retrieval occasionally returned stale embeddings after knowledge base updates. | S4 | Jasir Ahamed | Data/Logic Error | Added explicit collection refresh/re-index step after each knowledge base update job. | 27-Jul-2026 | Closed | Retrieval verified to reflect latest knowledge base content.