## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Requirement gathering and problem statement definition for Clario (AI-powered real-time customer support coaching assistant) | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S1 | S1 | US-002 | Workflow creation, system architecture design and project goal document | MUST HAVE | Lucid Chart | Jasir Ahamed | 3- Completed
S1 | S1 | US-003 | Document discussion (Agile Template, Defect Tracker, Unit Test Plan) | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S2 | S2 | US-004 | Tech stack finalization: FastAPI, React/TypeScript/Vite/Tailwind, MongoDB, ChromaDB | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S2 | S2 | US-005 | Setup FastAPI backend project structure and MongoDB connection | MUST HAVE | MongoDB Atlas | Jasir Ahamed | 3- Completed
S2 | S2 | US-006 | Setup React/TypeScript/Vite/Tailwind frontend project structure | MUST HAVE | Node.js, Vite | Jasir Ahamed | 3- Completed
S3 | S3 | US-007 | Integrate Groq API (Llama 3.3 70B) for Simulator Agent (customer conversation simulation) | MUST HAVE | Groq API | Jasir Ahamed | 3- Completed
S3 | S3 | US-008 | Integrate Groq API for Intent/Sentiment Analysis Agent | MUST HAVE | Groq API | Jasir Ahamed | 3- Completed
S3 | S3 | US-009 | Integrate Google Gemini API for Knowledge Agent (RAG-based knowledge retrieval) | MUST HAVE | Gemini API, ChromaDB | Jasir Ahamed | 3- Completed
S4 | S4 | US-010 | Integrate Google Gemini API for Coaching Agent (real-time coaching suggestions) | MUST HAVE | Gemini API | Jasir Ahamed | 3- Completed
S4 | S4 | US-011 | Integrate Google Gemini API for Escalation Agent and Summary Agent | MUST HAVE | Gemini API | Jasir Ahamed | 3- Completed
S4 | S4 | US-012 | Setup ChromaDB vector store for RAG pipeline and knowledge base embeddings | MUST HAVE | ChromaDB | Jasir Ahamed | 3- Completed
S5 | S5 | US-013 | Build multi-agent orchestration pipeline connecting Simulator, Intent/Sentiment, Knowledge, Coaching, Escalation and Summary agents | MUST HAVE | US-007 to US-012 | Jasir Ahamed | 3- Completed
S5 | S5 | US-014 | Implement session persistence using global SessionContext with useReducer | MUST HAVE | React Context API | Jasir Ahamed | 3- Completed
S5 | S5 | US-015 | Design and build real-time chat/coaching UI with live agent feedback panel | MUST HAVE | Tailwind CSS | Jasir Ahamed | 3- Completed
S6 | S6 | US-016 | Implement Manual Mode (agent-guided manual conversation handling) | SHOULD HAVE | US-013 | Jasir Ahamed | 3- Completed
S6 | S6 | US-017 | Implement Replay Mode (review and replay past coaching sessions) | SHOULD HAVE | US-013, MongoDB | Jasir Ahamed | 3- Completed
S6 | S6 | US-018 | Workflow automation and optimization across agent pipeline | SHOULD HAVE | VS Code | Jasir Ahamed | 3- Completed
S7 | S7 | US-019 | Fix pipeline ordering bug - Intent/Sentiment analysis executing before Simulator message generation (one-turn lag) | MUST HAVE | US-013 | Jasir Ahamed | 3- Completed
S7 | S7 | US-020 | Fix turn index collision causing duplicate turn labels in generated reports | MUST HAVE | MongoDB schema | Jasir Ahamed | 3- Completed
S7 | S7 | US-021 | Fix markdown bleed-through in coaching agent output rendering | SHOULD HAVE | Frontend renderer | Jasir Ahamed | 3- Completed
S7 | S7 | US-022 | Fix report _id mismatch breaking UI report-selection state | MUST HAVE | MongoDB, React state | Jasir Ahamed | 3- Completed
S7 | S7 | US-023 | Resolve blocking synchronous calls on the async FastAPI event loop | MUST HAVE | FastAPI, asyncio | Jasir Ahamed | 3- Completed
S8 | S8 | US-024 | Full repository audit and end-to-end testing across all four milestones | MUST HAVE | US-001 to US-023 | Jasir Ahamed | 3- Completed
S8 | S8 | US-025 | Generate 17-page professional PDF project report with custom SVG architecture diagrams | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S8 | S8 | US-026 | Prepare 15-page Word technical report and one-page demonstration handout | MUST HAVE | No Dependency | Jasir Ahamed | 3- Completed
S8 | S8 | US-027 | Deployment and final submission to Infosys team via GitHub repository | MUST HAVE | Render/Hosting | Jasir Ahamed | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (in Hours) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 BACKLOG ¦ 11-Jul-2026 to 16-Jul-2026
US-001 | T-001 | Requirement gathering and problem statement definition for Clario (AI-powered real-time customer support coaching assistant) | 2026-07-11 | 2026-07-14 | Jasir Ahamed | Requirements & problem definition | 3- Completed | 8 | 0 | 2 | 2 | 2 | 2 | 0
US-002 | T-002 | Workflow creation, system architecture design and project goal document | 2026-07-12 | 2026-07-16 | Jasir Ahamed | Workflow & architecture | 3- Completed | 10 | 2 | 0 | 2 | 2 | 2 | 2
US-003 | T-003 | Document discussion (Agile Template, Defect Tracker, Unit Test Plan) | 2026-07-13 | 2026-07-15 | Jasir Ahamed | Agile/document setup | 3- Completed | 6 | 0 | 0 | 0 | 6 | 0 | 0
S2 BACKLOG ¦ 17-Jul-2026 to 22-Jul-2026
US-004 | T-004 | Tech stack finalization: FastAPI, React/TypeScript/Vite/Tailwind, MongoDB, ChromaDB | 2026-07-17 | 2026-07-19 | Jasir Ahamed | Technology selection | 3- Completed | 6 | 0 | 0 | 0 | 0 | 6 | 0
US-005 | T-005 | Setup FastAPI backend project structure and MongoDB connection | 2026-07-18 | 2026-07-22 | Jasir Ahamed | Backend foundation | 3- Completed | 10 | 2 | 2 | 2 | 2 | 0 | 2
US-006 | T-006 | Setup React/TypeScript/Vite/Tailwind frontend project structure | 2026-07-19 | 2026-07-22 | Jasir Ahamed | Frontend foundation | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0
S3 BACKLOG ¦ 23-Jul-2026 to 28-Jul-2026
US-007 | T-007 | Integrate Groq API (Llama 3.3 70B) for Simulator Agent (customer conversation simulation) | 2026-07-23 | 2026-07-28 | Jasir Ahamed | Customer Simulator Agent | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
US-008 | T-008 | Integrate Groq API for Intent/Sentiment Analysis Agent | 2026-07-24 | 2026-07-28 | Jasir Ahamed | Intent & Sentiment Agent | 3- Completed | 10 | 2 | 0 | 2 | 2 | 2 | 2
US-009 | T-009 | Integrate Google Gemini API for Knowledge Agent (RAG-based knowledge retrieval) | 2026-07-25 | 2026-07-28 | Jasir Ahamed | Knowledge Agent / RAG | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
S4 BACKLOG ¦ 29-Jul-2026 to 03-Aug-2026
US-010 | T-010 | Integrate Google Gemini API for Coaching Agent (real-time coaching suggestions) | 2026-07-29 | 2026-08-02 | Jasir Ahamed | Coaching Agent | 3- Completed | 10 | 2 | 2 | 2 | 0 | 2 | 2
US-011 | T-011 | Integrate Google Gemini API for Escalation Agent and Summary Agent | 2026-07-30 | 2026-08-03 | Jasir Ahamed | Escalation & Summary Agents | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
US-012 | T-012 | Setup ChromaDB vector store for RAG pipeline and knowledge base embeddings | 2026-07-31 | 2026-08-03 | Jasir Ahamed | ChromaDB / embeddings | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0
S5 BACKLOG ¦ 04-Aug-2026 to 09-Aug-2026
US-013 | T-013 | Build multi-agent orchestration pipeline connecting Simulator, Intent/Sentiment, Knowledge, Coaching, Escalation and Summary agents | 2026-08-04 | 2026-08-09 | Jasir Ahamed | Multi-agent orchestration | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
US-014 | T-014 | Implement session persistence using global SessionContext with useReducer | 2026-08-05 | 2026-08-09 | Jasir Ahamed | Session persistence | 3- Completed | 10 | 2 | 0 | 2 | 2 | 2 | 2
US-015 | T-015 | Design and build real-time chat/coaching UI with live agent feedback panel | 2026-08-06 | 2026-08-09 | Jasir Ahamed | Live coaching UI | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
S6 BACKLOG ¦ 10-Aug-2026 to 15-Aug-2026
US-016 | T-016 | Implement Manual Mode (agent-guided manual conversation handling) | 2026-08-10 | 2026-08-13 | Jasir Ahamed | Manual mode | 3- Completed | 8 | 2 | 2 | 0 | 0 | 2 | 2
US-017 | T-017 | Implement Replay Mode (review and replay past coaching sessions) | 2026-08-11 | 2026-08-14 | Jasir Ahamed | Replay mode | 3- Completed | 8 | 2 | 2 | 2 | 0 | 0 | 2
US-018 | T-018 | Workflow automation and optimization across agent pipeline | 2026-08-12 | 2026-08-15 | Jasir Ahamed | Workflow optimization | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0
S7 BACKLOG ¦ 16-Aug-2026 to 21-Aug-2026
US-019 | T-019 | Fix pipeline ordering bug - Intent/Sentiment analysis executing before Simulator message generation (one-turn lag) | 2026-08-16 | 2026-08-19 | Jasir Ahamed | Pipeline ordering defect fix | 3- Completed | 8 | 0 | 2 | 2 | 2 | 2 | 0
US-020 | T-020 | Fix turn index collision causing duplicate turn labels in generated reports | 2026-08-17 | 2026-08-19 | Jasir Ahamed | Turn index/report defect fix | 3- Completed | 6 | 0 | 0 | 6 | 0 | 0 | 0
US-021 | T-021 | Fix markdown bleed-through in coaching agent output rendering | 2026-08-18 | 2026-08-20 | Jasir Ahamed | Markdown rendering defect fix | 3- Completed | 6 | 0 | 0 | 0 | 6 | 0 | 0
US-022 | T-022 | Fix report _id mismatch breaking UI report-selection state | 2026-08-19 | 2026-08-21 | Jasir Ahamed | Report ID/state defect fix | 3- Completed | 6 | 0 | 0 | 0 | 0 | 6 | 0
US-023 | T-023 | Resolve blocking synchronous calls on the async FastAPI event loop | 2026-08-20 | 2026-08-21 | Jasir Ahamed | Async FastAPI optimization | 3- Completed | 8 | 2 | 2 | 2 | 0 | 0 | 2
S8 BACKLOG ¦ 22-Aug-2026 to 28-Aug-2026
US-024 | T-024 | Full repository audit and end-to-end testing across all four milestones | 2026-08-22 | 2026-08-26 | Jasir Ahamed | Repository audit & E2E testing | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0
US-025 | T-025 | Generate 17-page professional PDF project report with custom SVG architecture diagrams | 2026-08-23 | 2026-08-28 | Jasir Ahamed | Professional PDF report | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
US-026 | T-026 | Prepare 15-page Word technical report and one-page demonstration handout | 2026-08-24 | 2026-08-28 | Jasir Ahamed | Technical report & handout | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2
US-027 | T-027 | Deployment and final submission to Infosys team via GitHub repository | 2026-08-25 | 2026-08-28 | Jasir Ahamed | Deployment & final submission | 2- In Progress | 10 | 2 | 2 | 0 | 2 | 2 | 2
TOTAL

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Requirements unclear at start | Defined problem statement and user stories; aligned scope to Clario coaching assistant.
S1 | Day 2 | Architecture dependencies | Documented workflow and system architecture before implementation.
S1 | Day 3 | Agile artifacts not yet organized | Created Product Backlog, Sprint Backlog, Defect Tracker and Unit Test Plan structure.
S1 | Day 4 | Backend pipeline setup | Resolved initial backend pipeline issues and validated FastAPI foundation.
S1 | Day 5 | Frontend/backend alignment | Validated initial UI/backend integration points.
S1 | Day 6 | Milestone 1 stabilization | Fixed confidence-score issue and prepared milestone documentation.
S2 | Day 1 | Agent integration sequencing | Implemented simulator and knowledge-recovery work in small increments.
S2 | Day 2 | Two-agent coordination | Validated Simulator and Knowledge Agent behavior together.
S2 | Day 3 | Agent response reliability | Iterated on prompts and API integration until responses were stable.
S2 | Day 4 | Three-agent integration | Validated Simulator, Intent/Sentiment and Knowledge stages.
S2 | Day 5 | Session continuity | Introduced stored-session handling for ongoing conversations.
S2 | Day 6 | Milestone 2 completion pressure | Completed milestone validation and Live Console updates.
S3 | Day 1 | Loading state could stall | Investigated and isolated the loading-state behavior.
S3 | Day 2 | Live Console still evolving | Updated Live Console while preserving existing agent outputs.
S3 | Day 3 | Session reuse needed | Moved conversation flow toward previously created session records.
S3 | Day 4 | Milestone 2 cleanup | Completed remaining integration and stability work.
S3 | Day 5 | Loading issue persisted | Applied additional loading-state fixes.
S3 | Day 6 | Sprint review | Verified milestone 2 behavior and documented next-step work.
S4 | Day 1 | Frontend integration complexity | Refined Live Console and state-management boundaries.
S4 | Day 2 | Session state duplication risk | Prepared a single source of truth for session configuration.
S4 | Day 3 | Global state requirement | Designed SessionContext/useReducer approach.
S4 | Day 4 | Navigation could lose active session | Moved active session state above routing.
S4 | Day 5 | UI feedback synchronization | Aligned turn status and live agent output handling.
S4 | Day 6 | Sprint review | Confirmed session persistence direction and prepared milestone 3.
S5 | Day 1 | Milestone 3 pipeline defects | Corrected customer-message persistence and pipeline sequencing.
S5 | Day 2 | Duplicate customer-message writes | Made conversation.py the single writer for customer messages.
S5 | Day 3 | Simulator stale-message issue | Removed dead SSE path and stale fallback behavior.
S5 | Day 4 | Coaching/Escalation placeholders | Wired live SessionContext data into coaching and escalation views.
S5 | Day 5 | Agent response latency | Investigated slow responses and optimized the milestone 3 flow.
S5 | Day 6 | Frontend polishing and bug fixes | Completed key console, escalation and simulator fixes.
S6 | Day 1 | UI design consistency | Established a shared design-token system.
S6 | Day 2 | Navigation styling changes | Applied consistent active-state styling and session indicator.
S6 | Day 3 | Live Console visual complexity | Restyled the four-panel console and responsive states.
S6 | Day 4 | Dashboard consistency | Restyled Analytics and supporting pages using shared tokens.
S6 | Day 5 | Regression risk from UI changes | Kept changes focused on styling without structural rewrites.
S6 | Day 6 | Sprint review | Completed major frontend polish and prepared mode enhancements.
S7 | Day 1 | Manual/Replay modes not yet available | Implemented Manual Mode for agent-guided conversations.
S7 | Day 2 | Replay workflow needed | Implemented replay of previous coaching sessions.
S7 | Day 3 | Milestone 4 integration | Connected new modes to existing session and coaching workflow.
S7 | Day 4 | Pipeline ordering defects | Validated Simulator generation before Intent/Sentiment analysis.
S7 | Day 5 | Report integrity issues | Fixed turn-index collisions and report identifier/state mismatches.
S7 | Day 6 | Async performance risk | Removed blocking synchronous work from FastAPI event loop.
S8 | Day 1 | Final audit scope large | Ran repository-wide review across four milestones.
S8 | Day 2 | Documentation workload | Prepared professional project documentation and architecture material.
S8 | Day 3 | Technical report preparation | Prepared technical report and demonstration handout.
S8 | Day 4 | Submission artifacts | Uploaded Agile, Defect Tracker and Unit Test sheets.
S8 | Day 5 | Final repository cleanup | Updated README/documentation and checked project structure.
S8 | Day 6 | Final deployment/submission step | Prepared final submission through the GitHub repository.

## Retrospective
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-07-11 | 2026-07-16 | Jasir Ahamed | Improve early requirement decomposition and estimation | Delay artifact setup until implementation starts | Keep architecture-first planning and clear must-have scope | Backlog and supporting Agile artifacts established.
2 | S2 | 2026-07-17 | 2026-07-22 | Jasir Ahamed | Break agent integration into independently testable increments | Make large integration changes without checkpoints | Validate each agent before orchestration | Added simulator, knowledge and intent/sentiment stages incrementally.
3 | S3 | 2026-07-23 | 2026-07-28 | Jasir Ahamed | Use session/state diagrams before UI integration | Rely on transient request state | Keep backend and frontend contracts explicit | Moved toward stored-session source of truth and stabilized Live Console.
4 | S4 | 2026-07-29 | 2026-08-03 | Jasir Ahamed | Centralize session state and turn lifecycle | Duplicate state across pages/components | Use SessionContext and reducer-based state | Implemented persistent global session context.
5 | S5 | 2026-08-04 | 2026-08-09 | Jasir Ahamed | Add defect-focused verification after each pipeline change | Allow UI/backend bugs to accumulate | Use fail-safe agent wrappers and targeted fixes | Fixed sequencing, duplicate writes, typewriter, auto-scroll and escalation issues.
6 | S6 | 2026-08-10 | 2026-08-15 | Jasir Ahamed | Use shared design tokens before page-level styling | Repeat one-off visual styles | Keep UI changes structurally conservative | Established token system and restyled core console/dashboard pages.
7 | S7 | 2026-08-16 | 2026-08-21 | Jasir Ahamed | Plan mode-specific acceptance scenarios | Treat Manual/Replay as isolated UI features | Reuse shared session/coaching infrastructure | Implemented Manual and Replay modes and stabilized milestone 4.
8 | S8 | 2026-08-22 | 2026-08-28 | Jasir Ahamed | Create final documentation alongside development | Leave reporting and submission work to the final day | Maintain repository as the source of truth | Completed audit, documentation, Agile artifacts and final submission preparation.

## Version History
CLARIO — VERSION HISTORY & DEVELOPMENT ACTIVITY
Project | Clario — AI-Powered Real-Time Customer Support Coaching Assistant
Repository | JasirAhamed786/Infosys-RAG-Project
Branch | master
GitHub commit count | 79 commits
Latest repository activity | 28-Aug-2026
Milestone structure | Four development milestones + final documentation/submission
Versioning note | No Git tags/releases were found; version stage below is inferred from commit activity.
Commit-level history
Version / Stage | Date | Commit SHA | Commit Message | Activity Type | Activity / Milestone | Outcome / Interpretation | GitHub Commit
V4.1 — Finalization | 2026-08-28 | 65d87a3 | Uploaded agile,defect tracker, unit test sheets | Documentation / Governance | V4.1 — Finalization development activity | Added project Agile/quality-management deliverables. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/65d87a3
V4.1 — Finalization | 2026-08-28 | 42b68df | Documentation uploaded | Documentation / Governance | V4.1 — Finalization development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/42b68df
V4.1 — Finalization | 2026-08-26 | 069dfe1 | Created Project Documentation | Documentation / Governance | V4.1 — Finalization development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/069dfe1
V4.1 — Finalization | 2026-08-26 | aa88e83 | Created final updated Readme.md | Documentation / Governance | V4.1 — Finalization development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/aa88e83
V4.1 — Finalization | 2026-08-26 | 1451cd6 | Created final Readme.md | Documentation / Governance | V4.1 — Finalization development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/1451cd6
V4 — Milestone 4 | 2026-08-21 | 656323d | Done some fixex on milestone 4 | Milestone Development | V4 — Milestone 4 development activity | Advanced final interaction modes and milestone-4 functionality. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/656323d
V4 — Milestone 4 | 2026-08-21 | 26b6fd4 | Edit by gemini code but not efficoent working | Development Iteration | V4 — Milestone 4 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/26b6fd4
V4 — Milestone 4 | 2026-08-21 | 4837fec | inbetween commit on milestone 4 | Milestone Development | V4 — Milestone 4 development activity | Advanced final interaction modes and milestone-4 functionality. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/4837fec
V4 — Milestone 4 | 2026-08-21 | 17c2335 | Implemented milestone 4 but not tested yet | Milestone Development | V4 — Milestone 4 development activity | Advanced final interaction modes and milestone-4 functionality. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/17c2335
V4 — Milestone 4 | 2026-08-19 | 74aabf2 | Inbetween commit2 on milestone 3 | Milestone Development | V4 — Milestone 4 development activity | Advanced or stabilized the live multi-agent coaching pipeline. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/74aabf2
V4 — Milestone 4 | 2026-08-19 | a91ee85 | Inbetween commit on milestone 3 | Milestone Development | V4 — Milestone 4 development activity | Advanced or stabilized the live multi-agent coaching pipeline. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/a91ee85
V4 — Milestone 4 | 2026-08-19 | 64a39af | Implemented manual and replay mode and they are working | Development Iteration | V4 — Milestone 4 development activity | Implemented or prepared Manual and Replay interaction modes. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/64a39af
V4 — Milestone 4 | 2026-08-16 | 7e1bd80 | going to implement manual and replay mode | Development Iteration | V4 — Milestone 4 development activity | Implemented or prepared Manual and Replay interaction modes. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/7e1bd80
V3 — Milestone 3 | 2026-08-09 | b265576 | README.md udpdated4 | Documentation / Governance | V3 — Milestone 3 development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/b265576
V3 — Milestone 3 | 2026-08-09 | 9e0ddbb | README.md udpdated3 | Documentation / Governance | V3 — Milestone 3 development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/9e0ddbb
V3 — Milestone 3 | 2026-08-09 | 525268d | README.md udpdated2 | Documentation / Governance | V3 — Milestone 3 development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/525268d
V3 — Milestone 3 | 2026-08-09 | 865cd01 | README.md udpdated | Documentation / Governance | V3 — Milestone 3 development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/865cd01
V3 — Milestone 3 | 2026-08-09 | 6d5e75b | fix(home): keep + reattach gradient bar to hero rounded border (Fix 5) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/6d5e75b
V3 — Milestone 3 | 2026-08-09 | 6dbf4c4 | fix(session): remove redundant mode label below dropdown (Fix 4) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/6dbf4c4
V3 — Milestone 3 | 2026-08-09 | 8859038 | fix(upload): increase Upload button contrast/saturation vs disabled state (Fix 3) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/8859038
V3 — Milestone 3 | 2026-08-09 | 72767ea | fix(console): send icon + chat bottom padding (Fix 1 & 2) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/72767ea
V3 — Milestone 3 | 2026-08-09 | 7ab867b | MIT licens addede | Development Iteration | V3 — Milestone 3 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/7ab867b
V3 — Milestone 3 | 2026-08-09 | 062bce4 | Milestone 3 working properly | Milestone Development | V3 — Milestone 3 development activity | Advanced or stabilized the live multi-agent coaching pipeline. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/062bce4
V3 — Milestone 3 | 2026-08-09 | 62db2fa | docs: mark Bug 1-4 fixes complete in tracking | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/62db2fa
V3 — Milestone 3 | 2026-08-09 | 4a219c6 | fix(simulator): prompt only - instruct realistic short casual customer texts (1-3 sentences, occasional imperfection) (Bug 4) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/4a219c6
V3 — Milestone 3 | 2026-08-09 | 2faeb52 | fix(console): optimistic UI for agent message with Sending/Failed states (Bug 3) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/2faeb52
V3 — Milestone 3 | 2026-08-09 | 4149317 | fix(console): only auto-scroll chat to bottom when a new message arrives and user is near bottom (Bug 2) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/4149317
V3 — Milestone 3 | 2026-08-09 | 86a5cb1 | fix(escalation): derive risk_level from score server-side and scale escalation_risk to 0-100 (Bug 1) | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/86a5cb1
V3 — Milestone 3 | 2026-08-09 | 5a043a9 | Frontend polished more | Frontend / UX | V3 — Milestone 3 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/5a043a9
V3 — Milestone 3 | 2026-08-09 | 9533cc7 | Frontend polished | Frontend / UX | V3 — Milestone 3 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/9533cc7
V3 — Milestone 3 | 2026-08-09 | 117f26a | Frontendd polishing | Frontend / UX | V3 — Milestone 3 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/117f26a
V3 — Milestone 3 | 2026-08-09 | 8d2aca7 | overhaul: shift to deep corporate navy accent (ACCA-style) and tokenize Home page | Development Iteration | V3 — Milestone 3 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/8d2aca7
V3 — Milestone 3 | 2026-08-09 | 7faa2d2 | docs: mark UI overhaul Tasks 5 & 6 complete in tracker | Documentation / Governance | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/7faa2d2
V3 — Milestone 3 | 2026-08-09 | c6ab79a | Task 6: restyle Analytics Dashboard in place - token colors/spacing/typography/borders only, no structural changes | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/c6ab79a
V3 — Milestone 3 | 2026-08-09 | 77e27aa | Task 5: restyle SessionConfig, KnowledgeBaseUpload, ComingSoonBase, CoachingFeed, EscalationAlerts, Reports onto design token system | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/77e27aa
V3 — Milestone 3 | 2026-08-09 | ec39b86 | Task 4: restyle Live Console onto token system (4-panel grid, chat bubbles, risk colors, calm pending/error states, responsive stacking) | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/ec39b86
V3 — Milestone 3 | 2026-08-09 | 0a530e6 | Task 3: restyle top navigation to single accent active state with subtle tint + underline, persistent session indicator | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/0a530e6
V3 — Milestone 3 | 2026-08-09 | 56c4315 | Task 2: establish global Clario design token system (colors, spacing, fonts) and flatten decorative global styling | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/56c4315
V3 — Milestone 3 | 2026-08-09 | 4222fd7 | fixing slow | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/4222fd7
V3 — Milestone 3 | 2026-08-09 | f064426 | In milestone three, everything is working, but it is very slow the agent response. | AI Agent Development | V3 — Milestone 3 development activity | Investigated or improved runtime responsiveness/reliability. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/f064426
V3 — Milestone 3 | 2026-08-08 | 036fe73 | Still working on milestone 3 | Milestone Development | V3 — Milestone 3 development activity | Advanced or stabilized the live multi-agent coaching pipeline. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/036fe73
V3 — Milestone 3 | 2026-08-08 | 81b656f | task 5: wire real coaching + escalation stages into orchestration pipeline | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/81b656f
V3 — Milestone 3 | 2026-08-08 | 83d7be4 | task 4: build real escalation_agent.py with Gemini - strict JSON escalation risk with _safe_run_agent-style fallback only on API error | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/83d7be4
V3 — Milestone 3 | 2026-08-08 | 4a01b32 | task 3: build real coaching_agent.py with Gemini - strict JSON coaching suggestion with _safe_run_agent-style fallback only on API error | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/4a01b32
V3 — Milestone 3 | 2026-08-08 | ec28f48 | task 2: Fix Bug A - backend start_simulator and conversation_turn now use stored session doc as source of truth, falling back to request body only when missing | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/ec28f48
V3 — Milestone 3 | 2026-08-08 | 95a7a02 | task 1: Fix Bug B - remove dead SSE read-path and 'I need assistance.' fallback in simulator.py so pipeline generates fresh customer message | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/95a7a02
V3 — Milestone 3 | 2026-08-08 | 603a187 | fix (issue 2): rework typewriter to identity-based re-arm + remove duplicate typing bubble in LiveConsole | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/603a187
V3 — Milestone 3 | 2026-08-08 | 44db305 | Milestone 3 working | Milestone Development | V3 — Milestone 3 development activity | Advanced or stabilized the live multi-agent coaching pipeline. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/44db305
V3 — Milestone 3 | 2026-08-08 | 2dd1437 | fix (issue 4): make conversation.py single writer for customer messages - remove double-persist in simulator_agent.py | Defect Fix / Stabilization | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/2dd1437
V3 — Milestone 3 | 2026-08-08 | a9bf526 | task 6: add MILESTONE3_FRONTEND_LOG.md | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/a9bf526
V3 — Milestone 3 | 2026-08-08 | 72bda20 | task 5: wire CoachingFeed + EscalationAlerts placeholders to live SessionContext | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/72bda20
V3 — Milestone 3 | 2026-08-08 | 6ab3869 | task 4: migrate LiveConsole to SessionContext, drop SSE, add client-side typewriter + turnStatus | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/6ab3869
V3 — Milestone 3 | 2026-08-08 | 1cb797d | task 3: wrap app with SessionProvider | Implementation Task | V3 — Milestone 3 development activity | Completed a focused implementation or UI task. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/1cb797d
V3 — Milestone 3 | 2026-08-08 | 4bda9a3 | task 2: SessionContext with turnCount fix and config persistence | Implementation Task | V3 — Milestone 3 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/4bda9a3
V2 — Milestone 2 | 2026-07-28 | 7be5960 | Loading stuck nearly fixed | Performance / Reliability | V2 — Milestone 2 development activity | Resolved a targeted functional, UI, data-flow or reliability issue. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/7be5960
V2 — Milestone 2 | 2026-07-28 | 3482878 | Working on loading stuck | Performance / Reliability | V2 — Milestone 2 development activity | Investigated or improved runtime responsiveness/reliability. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/3482878
V2 — Milestone 2 | 2026-07-27 | 6e6c6b1 | updated code for using the previously created session using session module | Session / State Management | V2 — Milestone 2 development activity | Improved persistence and consistency of active conversation state. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/6e6c6b1
V2 — Milestone 2 | 2026-07-27 | da60ce9 | Inbetween commit for milestone 2 | Milestone Development | V2 — Milestone 2 development activity | Advanced the multi-agent workflow and session/live-console implementation. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/da60ce9
V2 — Milestone 2 | 2026-07-26 | 163f220 | Liveconsole page updating | Frontend / UX | V2 — Milestone 2 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/163f220
V2 — Milestone 2 | 2026-07-26 | 0054150 | All 3 agents for milestone 2 working perfectly | AI Agent Development | V2 — Milestone 2 development activity | Advanced the multi-agent workflow and session/live-console implementation. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/0054150
V2 — Milestone 2 | 2026-07-26 | abd3c6b | Milestone two nearly completed, agents are working | AI Agent Development | V2 — Milestone 2 development activity | Advanced the multi-agent workflow and session/live-console implementation. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/abd3c6b
V2 — Milestone 2 | 2026-07-26 | ae32b7d | Simulator agent is working perfectly | AI Agent Development | V2 — Milestone 2 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/ae32b7d
V2 — Milestone 2 | 2026-07-25 | fb2c537 | 2 agents working (simulator and Knowledge recovery | AI Agent Development | V2 — Milestone 2 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/fb2c537
V2 — Milestone 2 | 2026-07-25 | 0cdd5e0 | Working on milestone 2 a | Milestone Development | V2 — Milestone 2 development activity | Advanced the multi-agent workflow and session/live-console implementation. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/0cdd5e0
V2 — Milestone 2 | 2026-07-25 | 5b8481d | Working on milestone 2 | Milestone Development | V2 — Milestone 2 development activity | Advanced the multi-agent workflow and session/live-console implementation. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/5b8481d
V2 — Milestone 2 | 2026-07-25 | a4d9ac7 | Inbetween commit 123 | Development Iteration | V2 — Milestone 2 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/a4d9ac7
V1 — Milestone 1 | 2026-07-14 | e8993de | Inbetween commit 2 | Development Iteration | V1 — Milestone 1 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/e8993de
V1 — Milestone 1 | 2026-07-13 | 1cee736 | gitignore updated 2 | Repository Setup | V1 — Milestone 1 development activity | Updated repository configuration. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/1cee736
V1 — Milestone 1 | 2026-07-13 | 7807cf8 | gitignore updated | Repository Setup | V1 — Milestone 1 development activity | Updated repository configuration. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/7807cf8
V1 — Milestone 1 | 2026-07-12 | afcde82 | Inbetween commit | Development Iteration | V1 — Milestone 1 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/afcde82
V1 — Milestone 1 | 2026-07-12 | 94335ae | Readme updated for milestone 1 | Documentation / Governance | V1 — Milestone 1 development activity | Updated project documentation and delivery artifacts. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/94335ae
V1 — Milestone 1 | 2026-07-12 | 87a3cf9 | Homepage created | Frontend / UX | V1 — Milestone 1 development activity | Created the initial application homepage. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/87a3cf9
V1 — Milestone 1 | 2026-07-12 | e106354 | UI enhanced | Frontend / UX | V1 — Milestone 1 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/e106354
V1 — Milestone 1 | 2026-07-12 | 9a2f47f | Preparing environment for upcoming milestones | Milestone Development | V1 — Milestone 1 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/9a2f47f
V1 — Milestone 1 | 2026-07-12 | 3371151 | Milestone 1 completed(just fixed confidence score) | Milestone Development | V1 — Milestone 1 development activity | Milestone 1 functionality reached a completed state. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/3371151
V1 — Milestone 1 | 2026-07-12 | ea82a97 | Milestone 1 completed | Milestone Development | V1 — Milestone 1 development activity | Milestone 1 functionality reached a completed state. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/ea82a97
V1 — Milestone 1 | 2026-07-11 | 6c41a55 | FASTAPI works | Development Iteration | V1 — Milestone 1 development activity | Confirmed FastAPI backend foundation was operational. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/6c41a55
V1 — Milestone 1 | 2026-07-11 | 221a655 | Resolved backend pipeline | Development Iteration | V1 — Milestone 1 development activity | Recorded an incremental development change. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/221a655
V1 — Milestone 1 | 2026-07-11 | 3ada8d1 | Initial commit for Milestone 1 | Milestone Development | V1 — Milestone 1 development activity | Established the initial milestone implementation baseline. | https://github.com/JasirAhamed786/Infosys-RAG-Project/commit/3ada8d1
Source: public GitHub repository history and README/project structure. Stand-up and retrospective records in this workbook are reconstructed project-management entries based on the repository activity, not verbatim meeting minutes.